MFO Change Management SOP (vNext)

Multinational Force and Observers (MFO)

Effective Date: <to be confirmed>  |  Owner: CJ6 / DCIO  |  Version: 1.0

Table of Contents

1.Purpose and Scope	2

2. References	2

3. Roles and RACI	2

4. Prerequisites	4

5. Workflow Overview	4

5.1	Request Capture (SWSD)	4

5.2	Triage and Categorization	4

5.3	Impact Analysis and Risk Assessment	4

5.4	Approval Routing	4

5.5	Implementation Planning	5

5.6	Pre-Change Communication	5

5.7	Implementation	5

5.8	Validation and Core	5

5.9	Post-Implementation Review (PIR)	6

6. Emergency Change Procedure (Abbreviated)	6

7. Evidence & Records	6

8. Checklist and Templates	6

8.1	Request Capture Checklist	6

8.2	Implementation Readiness Checklist	6

8.3	PIR Checklist	6

9. Metrics & Reporting	7

10.SOP Review & Maintenance	7

# 1.Purpose and Scope

This SOP operationalizes the Change Management Policy: it defines how to request, assess, approve, implement, validate, and record changes to MFO ICT systems using SolarWinds Service Desk (SWSD) as the system of record.

# 2. References

MFO Change Management Policy (vNext)

SWSD Change Management module (system of record)

Change Types & Approvers matrix (Emergency/Major/Normal/Minor/Standard/Maintenance/Non‑ICT)

Directive 20‑01: Records Disposition Policy

Risk Management Policy (OPORD 02/20)

# 3. Roles and RACI

Roles

| Role / Group | Responsibilities |
| --- | --- |
| Requester | • Initiates the change in SWSD |
|  | • Provides baseline details and business justification |
| Section Manager (NCSM / ASM / RCM) | • Owns the change |
|  | • Completes the Specification |
|  | • Prepares the Risk Assessment (with ICT Security when needed) |
|  | • Develops the Implementation Plan, including testing & rollback steps |
| ICT Security | • Provides risk-based endorsement for Emergency and Major changes |
|  | • Endorses Normal changes affecting security controls, identity, or perimeter |
|  | • Acts in an advisory capacity for other change types |
| DCIO / CIO | • Approve changes per approval matrix |
|  | • May convene an ad-hoc CAB for Major or Emergency cases |
|  | • Provide governance oversight and manage escalations |
| Stakeholders / Testers | • Execute assigned test actions |
|  | • Provide required test evidence |

RACI (high‑level)

| Activity | Requester | Section Mgr | ICT Security | DCIO | CIO | Stakeholders |
| --- | --- | --- | --- | --- | --- | --- |
| Open CR in SWSD | R | A | C | I | I | I |
| Specification | C | A | C | I | I | I |
| Risk Assessment | C | A | C/R* | I | I | I |
| Implementation Plan (test & rollback) | C | A | C | I | I | C |
| Approval routing | I | R | C (risk‑based) | A/R | A/R | I |
| Pre‑change comms | I | A/R | C | I | I | C |
| Implementation | I | A/R | I | I | I | R |
| Validation & Closure | I | A/R | I | I | I | R |
| PIR (when required) | I | A/R | C | A/R | I | C |

* ICT Security provides a mandatory endorsement for Emergency/Major and for Normal where security controls/identity/perimeter are impacted.

# 4. Prerequisites

All changes must be recorded in SWSD; verbal approvals are not permitted.

Use Standard change catalogue where applicable (pre‑approved low‑risk items).

Ensure NTP time sync, logging, and evidence capture on systems to be changed.

# 5. Workflow Overview

# Request Capture (SWSD)

- Open a Change Request (CR) in SWSD using the standard form.

- Required fields (titles): Requester; System/CI; Change Type (Emergency/Major/Normal/Minor/Standard/Maintenance/Non‑ICT); Business Justification; Impacted Services; Risk Summary; Implementation Plan reference; Rollback Plan; Planned Window; Affected Stakeholders; Evidence Links.

# Triage and Categorization

- Section Manager verifies scope and selects Change Type and risk level per the Approvals matrix.

- If the request matches a Standard change, reference the catalogue ID and steps; otherwise proceed as Normal/Major/Emergency as appropriate.

# Impact Analysis and Risk Assessment

- Complete the Specification (what/why/where, interfaces, success criteria).

- Complete Risk Assessment (services impacted; confidentiality‑integrity‑availability; mitigations; back‑out).

- ICT Security endorsement: required for Emergency/Major and for Normal where security controls/identity/perimeter are impacted; advisory otherwise.

# Approval Routing

| Change Type | Approvals (sequence) | Notes |
| --- | --- | --- |
| Emergency | Section Manager → DCIO → CIO | Abbreviated documentation allowed prior to implementation; full artefacts within 2 business days |
| Major | Section Manager → DCIO → CIO | Ad‑hoc CAB may be convened by DCIO/CIO if needed |
| Normal | Section Manager → DCIO or CIO | Risk‑based Security endorsement as above |
| Minor | Section Manager → DCIO or CIO | Low‑risk localized changes |
| Standard | Section Manager (catalogue pre‑approved) | Follow documented steps and attach evidence |
| Maintenance/Non‑ICT | Informational (calendar only) | No approvals; communication only |

# Implementation Planning

- Finalize Implementation Plan including Test Plan and Rollback Strategy.

- Define maintenance window / blackout constraints and notify affected staff with assigned actions.

- Confirm validation checks and evidence required for closure.

# Pre-Change Communication

- Send email notifications to affected users/teams with timing, impact, and rollback contacts.

- Ensure service desk and on‑call rosters are aware; update outage/maintenance calendars.

# Implementation

- Execute steps as per Implementation Plan; record deviations in SWSD with reasons.

- If a deviation introduces risk, pause and seek updated approval or invoke rollback.

- For Emergency, follow the emergency path with immediate communication and post‑change completion of artefacts.

# Validation and Core

- Run validation checks; capture evidence (screenshots/logs/queries) in SWSD.

- Update CI records (CMDB) where applicable; link the CR to the CI in SWSD.

- Close the CR with outcomes, residual risks, and evidence links.

# Post-Implementation Review (PIR)

- Required for Emergency and Major within 10 business days; Normal at DCIO discretion; Minor/Standard not required unless impact/incident occurred.

- PIR agenda: what changed; outcomes vs. success criteria; deviations; lessons learned; follow‑up actions.

# 6. Emergency Change Procedure (Abbreviated)

Initiate Emergency CR in SWSD; include concise business justification and risk summary.

Obtain rapid approvals (Section Manager → DCIO → CIO) via SWSD; if verbally coordinated, record written approvals within CR immediately after.

Implement fix; communicate to impacted groups; validate services restored.

Within 2 business days: complete full artefacts (Specification, Risk, Implementation Plan, evidence) and hold PIR within 10 business days.

# 7. Evidence & Records

SWSD is the system of record for live change lifecycle and artefacts.

Closed change packages are exported monthly to ICT SharePoint and retained per Directive 20‑01.

Evidence to retain: Specification, Risk Assessment, approvals, Implementation Plan, notifications, validation evidence, PIR minutes (if applicable).

# 8. Checklist and Templates

# Request Capture Checklist

- Requester; System/CI; Change Type; Business Justification; Impacted services/users; Risk summary; Dependencies; Windows/blackouts; Implementation Plan/steps; Rollback; Stakeholders; Evidence links.

# Implementation Readiness Checklist

- Approvals obtained; test environment validated; backups/snapshots taken; monitoring/rollbacks prepared; communication sent; on‑call informed.

# PIR Checklist

- Success criteria met? unexpected impacts? deviations and reasons? control improvements? tickets/actions assigned with owners and due dates.

# 9. Metrics & Reporting

% Standard vs. Emergency vs. Normal/Major; change success/failure rate; PIR completion rate; mean time to implement; % with complete artefacts; % changes linked to CI records.

# 10. SOP Review & Maintenance

SOP reviewed annually alongside the Change Management Policy; after significant incidents or audit findings; and when SWSD workflow changes.